## Checklist
Prover Checklist from MERO-2 Punch List
Customer Name
Customer PO:
No | Description of Discrepancy | Yes/No | Comments
1 | Are there any AVL requirements; if yes, provide AVL | Yes | No material to be used from Ulma Cable glands supplier
2 | Motor must have direction arrow | Yes
3 | Motor must have orange end cover | Yes
4 | Motor, JB & control panel must have NR10warning labels | Yes
5 | Are there cable tray mounting requirements? (if yes, proivide requirements in comments) | Yes | Yes, As per Almirante/Mero-2
6 | Cable ties shall be SS with PVC/nylon coating | Yes
7 | cables shall have cable numbers installed at each end | Yes
8 | earth strap installed on the prover shall be Green/yellow | Yes
9 | Equipment earth cable shall be 6mm | Yes
10 | Cables shall be LSZH type | Yes | cable as per project specification
11 | manufacturer nameplate shall be dual language (If yes, provide language in comments) | Yes | Portuguese / English as per previous projects
12 | Control panel door must have earth cable | Yes
13 | Stuffing glands into the bottom of the NEMA 4X box must have a serrated/star washer installed | Yes
14 | Adaptors must be Metric to NPT for the cable glands | Yes
15 | Minimum allowed size for power cables is 2.5mm | Yes
16 | Motor power cable into the power control must be Brown, Black, Grey | Yes
17 | All cable cores must be terminated | Yes
18 | SVP controller box, motor controller, and terminal box must have tag installed with service description and TAG ID's (if yes, customer must provide all tag ID's prior to kick off meeting) | Yes