## Parts by Supplier
Free-Issued Parts to Honeywell/TruStop Factory - NOA & Valhall Fenris Provers
Reference Projects: SP-00525 (Hugin A / SVP050) & SP-00577 (Valhall Fenris / SVP015)
Prepared by Sifab AS - For reference on Snorre A SVP085 project (GM-8501-1447)
# | Supplier | Parts Supplied | Specification | Qty per Prover | Notes
1 | Draka | BFOU cables - optical switches | #20110634 (1 triple), BFOU(i) S3/S7/S103 250V | ~50m | For 3 optical switches on switch bar
2 | Draka | BFOU cables - motor stop switch | #20110623 (1 pair), BFOU(i) S3/S7/S103 250V | ~14m | For motor stop limit switch
3 | Draka | BFOU cables - temperature elements | #20110623 (1 pair) + #20110626 (2 pair) | ~20m each | JB to transmitter + transmitter to TE
4 | R. Stahl / Tranberg | Ex i terminal box (JB) | Type 8150/2-0360-0360-150-3311, SS 316L, IP66, Ex ia/ib IIC T5 Gb | 1 | Assembled by Tranberg in Norway
5 | Phoenix | Terminal blocks + jumpers | UT 2.5 BU terminal blocks, FPS jumpers | 37 blocks/JB | Installed inside JBs
6 | CMP | Cable glands, stopping plugs, drain plugs | A2F100 M32/M20, 757 M32/M20, 781E M20 - nickel-plated brass | ~11 per JB | Fitted in JBs
7 | B.F.E. / Bonney Forge (Italy) | 1/2" Double Block & Bleed valve | DN15, Duplex SS F51, NACE MR0175, extended handle for 100mm insulation | 1 | CL 150 (Valhall) / CL 300 (Hugin A). Via MRC Global Norway
8 | Pemberton Fabricators (NJ, USA) | Seraphin calibration cans | 151.4L (Hugin A) / 75.7L (Valhall). SS 316, NIST traceable | 1 | Calibrated by Pennsylvania Standards Lab (NVLAP 200869-0)
9 | Metallteknikk AS (Sandnes/Bryne) | SS 316L transport enclosures for Seraphin cans | Art. 143251 (1700x1000x1200mm, 235kg) / Art. 143252 (1620x850x1200mm, 208kg) | 1 | Designed by Sifab (Idar Eriksen). EMKA locks, forklift-liftable
10 | Lucifer (via Flowtec AS) | Solenoid valves for water draw kit | Model 201LG4SVG7, coil 492190C2, SS 316, 24VDC, 1/2" BSP, IP66, Ex eb mb IIC T3/T4 | 1 | Direct pilot operated, 2-port, spring return
11 | Hoke | Tubing fittings for water draw kit | 1" 6Mo tubing and fittings (upgraded from 1/2" via VOR 003) | Kit | 1" fittings 3x cost of 1/2". Larger bending radius required elbows
12 | Lanne Elektriske (Aker BP frame agr.) | Motor - ATB brand | 1 HP, 690VAC 60Hz 3ph (Valhall) / 690VAC 50Hz 3ph (Hugin A) | 1 | Non-standard motors per Aker BP frame agreement. Caused delays
13 | Sifab AS (fabricated) | Thermowells - Duplex SS | Per HW drawings. 1/2" NPTF, bore 6.5mm | 3 | Extra TW on switch bar for annual calibration
14 | Sifab AS (fabricated) | DBB valve adapter | 1/2" ANSI 600 x ANSI 150/300 (B16.5) | 1 | Adapts prover 600# connection to DBB valve class
15 | Sifab AS (fabricated) | Pipe stand for temperature transmitters | Custom bracket for mounting outside cabinet (insulation) | 1 | Added via VOR 003 - insulation required external mounting
16 | Sifab AS (fabricated) | Customer enclosure | SS 316 | 1 | Junction box mounting enclosure
17 | Sifab AS (purchased) | Bolts and nuts | Stud bolts + hex nuts per PCS AD20/BD20. Sizes: 1/2"-13, 5/8"-11 | 36-60 | All with MTR certificates
18 | Sifab AS (purchased) | Spiral wound gaskets | 1/2" 150#/300#/600# SS 316 | 6 (spares) | Sent as extra spares
19 | Sifab AS (purchased) | 6Mo Parker plugs | NPT plugs in 6Mo material | As needed | Replaced standard vent valves. Added via VOR 004
20 | Sifab AS (purchased) | Cable glands for instruments | M25/M20 with 90-deg elbows + straight, M20 adapters | ~12 | For temp transmitters, switches, JB entries
21 | FMC (free-issued direct) | 4-wire RTDs | Similar to HW P/N 44102764/44102765/44110604 | 3 | Sent direct from FMC manufacturer, not via Sifab
22 | FMC (free-issued direct) | Temperature transmitters | Prover TT, Switch bar TT, Extra TT | 3 | Sent direct from FMC manufacturer
23 | FMC (free-issued direct) | Pressure transmitters | Not in Honeywell scope - FMC installs | 1 | FMC responsibility

## Snorre A Checklist
Snorre A SVP085 - Procurement Checklist (Based on NOA/Valhall Experience)
Items Sifab will likely need to source and free-issue to Honeywell/TruStop
# | Item | Expected Spec (Snorre A) | Supplier (NOA/Valhall) | Action Required | Status
1 | BFOU cables (switches + temp + motor) | BFOU type per TR3023/E-001. Confirm lengths with HW GA | Draka | Get cable schedule from Honeywell after GA drawing | TBD
2 | Ex terminal box (JB) | Ex ia/ib IIC, SS 316L, IP66. Size TBD based on cable count | R. Stahl / Tranberg | Confirm JB size after wiring diagram | TBD
3 | Terminal blocks + jumpers | Phoenix UT 2.5 BU + FPS jumpers per termination diagram | Phoenix | Order after termination diagram approved | TBD
4 | Cable glands | M25/M20/M32 nickel-plated brass or SS 316 per E-001 | CMP | Confirm sizes with JB and instrument entries | TBD
5 | DBB valve | 1/2" CL 600 (BD20X), Duplex SS F51, NACE, extended for insulation | B.F.E. / Bonney Forge via MRC Global | LONG LEAD - order early. Confirm class with Guidant | TBD
6 | DBB valve adapter | 1/2" ANSI 600 adapter if needed | Sifab (fabricate) | Confirm if needed based on prover connection | TBD
7 | Seraphin can | Size TBD per SVP085 volume - likely larger than 151.4L | Pemberton Fabricators (NJ) | Get size from Honeywell. Justervesenet cert required | TBD
8 | Seraphin transport enclosure | SS 316L, sized for Seraphin can, forklift-liftable | Metallteknikk AS (Sandnes) | Design after can size confirmed | TBD
9 | Solenoid valve (water draw kit) | SS 316, 24VDC, Ex rated. Confirm orifice size early! | Lucifer via Flowtec AS | Specify orifice in initial design - avoid VOR | TBD
10 | Water draw kit tubing + fittings | 1" 6Mo (use 1" from start - lesson learned from VOR) | Hoke | Specify 1" from start - the upgrade was biggest VOR item | TBD
11 | Motor | 230VAC 3ph 60Hz (or 50Hz - TQ-001 pending) | Honeywell (standard) | If standard HW motor, no free-issue needed. Confirm freq | TBD
12 | Thermowells - Duplex SS | Per BD20X MDS. 1/2" NPTF, bore 6.5mm. 3x process + 1x rod | Sifab (fabricate) | Get TW drawings from HW. Fabricate in Norway, ship to AZ | TBD
13 | Bolts, nuts, gaskets | Per BD20X piping class (CL 600). Studs + hex nuts with MTRs | Sifab (purchase) | Get bolt list from HW after GA approved | TBD
14 | Pipe stand for temp transmitters | Custom bracket for external mounting (insulation) | Sifab (fabricate) | Include in initial design - was VOR on previous projects | TBD
15 | 6Mo Parker plugs | NPT plugs in 6Mo per TR2000 BD20X | Sifab (purchase) | Include from start - was VOR 004 on previous projects | TBD
16 | Temperature elements (RTDs) | 4-wire RTDs - Guidant free-issue per RFQ | Guidant (free-issue) | Confirm with Guidant - vendor installs TE but does not supply | TBD
17 | Temperature transmitters | Guidant free-issue per RFQ | Guidant (free-issue) | Confirm with Guidant | TBD